## Gantt Chart
FYP Gantt Chart |  | Smartsheet Tip ➜
Development of E-commerce Website for Maision Sakura Bakery |  | INTI INTERNATIONAL COLLEGE PENANG
19/5/25
|  | p1 | [11 empty] | p2
WBS NUMBER | TASK TITLE | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12 | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12
I | Research for project title | bar: p1 w1
II | Look for Supervisor to supervise the project | bar: p1 w1
III | Drafting initial form | bar: p1 w2
IV | Abstract | bar: p1 w3
1 | Introduction
1.1 | Introduction | bar: p1 w3
1.2 | Problem Statement | bar: p1 w3
1.3 | Detailed Research Questions | bar: p1 w3
1.4 | Objectives | bar: p1 w3
1.5 | Clients, Auduence & Motivation | bar: p1 w3
1.6 | scope of Project | bar: p1 w3 to p1 w4
1.8 | Conclusion | bar: p1 w3
2 | Literature Review
2.1 | Introduction | bar: p1 w4
2.2 | Defining the topic | bar: p1 w4 to p1 w6
2.3 | Study on the existing system/technology | bar: p1 w4 to p1 w6
2.4 | Comparison/summary of the existing system/technology | bar: p1 w4 to p1 w6
2.5 | Insights from Hogan Bakery, Lavender Bakers and Kenny Hills Bakers for Maison Sakura Bakery | bar: p1 w4 to p1 w6
2.6 | Review on System Methodologies | bar: p1 w7 to p1 w8
2.7 | Review on Development Tools | bar: p1 w8
2.8 | Conclusion | bar: p1 w4 to p1 w6; p1 w8
3 | System Methodologies
3.1 | Introduction | bar: p1 w9
3.2 | System Methodology | bar: p1 w9 to p1 w12
3.2.1 | Prepare Survey | bar: p1 w11
3.2.2 | Prepare Use Case Diagram | bar: p1 w11 to p1 w12
3.2.3 | Prepare ERD | bar: p1 w11 to p1 w12
3.2.4 | Prepare Flowchart | bar: p1 w11 to p1 w12
3.2.5 | Prepare Prototype
3.2.6 | Implementation
3.2.7 | System Testing
3.2.8 | Deployment
3.2.9 | Maintenance
3.3 | Conclusion
4 | Website Development
4.1 | Customer Register Page | bar: p2 w1 to p2 w9; p2 w12
4.2 | Customer Login Page | bar: p2 w1 to p2 w9; p2 w12
4.3 | Customer Home Page | bar: p2 w1 to p2 w9; p2 w12
4.4 | Customer Product Page | bar: p2 w3 to p2 w9; p2 w12
4.5 | Customer Cart Page | bar: p2 w4 to p2 w9; p2 w12
4.6 | Customer Checkout Page | bar: p2 w4 to p2 w9; p2 w12
4.7 | Customer Order Page | bar: p2 w4 to p2 w9; p2 w12
4.8 | Customer About Page | bar: p2 w5 to p2 w9; p2 w12
4.9 | Customer Contact Page | bar: p2 w5 to p2 w9; p2 w12
4.10 | Customer Profile Page | bar: p2 w4 to p2 w9; p2 w12
4.11 | Admin Register Page | bar: p2 w1 to p2 w9; p2 w12
4.12 | Admin Login Page | bar: p2 w1 to p2 w9; p2 w12
4.13 | Admin Home Page | bar: p2 w1 to p2 w9; p2 w12
4.14 | Admin Manage Order Page | bar: p2 w8 to p2 w9; p2 w12
4.15 | Admin Manage Product Page | bar: p2 w8 to p2 w9; p2 w12
4.16 | Admin Manage raw items Page | bar: p2 w8 to p2 w9; p2 w12
4.17 | Admin Manage Customer Page | bar: p2 w8 to p2 w9; p2 w12
4.18 | Admin Messages Page | bar: p2 w8 to p2 w9; p2 w12
4.19 | Admin Profile Page | bar: p2 w4 to p2 w9; p2 w12
4.20 | Superadmin Login Page | bar: p2 w1 to p2 w9; p2 w12
4.21 | Superadmin Home Page | bar: p2 w1 to p2 w9; p2 w12
4.22 | Superadmin Manage admin page | bar: p2 w9; p2 w12
4.23 | Superadmin audit log page | bar: p2 w9; p2 w12
4.24 | Superadmin report page | bar: p2 w9; p2 w12
5 | Project Implementation
5.1 | Introduction
5.2 | Implementation of Customer Page
5.3 | Implementation of Admin Page
5.4 | Implementation of Superadmin Page
5.5 | Branching Strategy
5.6 | Conclusion
6 | Testing & Analysis
6.1 | Introduction
6.2 | Testing Methods
6.3 | Unit Testing | bar: p2 w12
6.4 | Integration Testing | bar: p2 w12
6.4 | Performance Testing | bar: p2 w12
6.5 | Conclusion | bar: p2 w12
7 | Discussion
7.1 | Introduction | bar: p2 w12
7.2 | Achievements | bar: p2 w12
7.3 | Limitations | bar: p2 w12
7.4 | Future Enhancements | bar: p2 w12
7.5 | Conclusion | bar: p2 w12
8 | Reflection
8.1 | Introduction | bar: p2 w12
8.2 | Personal Reflection | bar: p2 w12
8.3 | Challenges & Solutions | bar: p2 w12
8.4 | Conclusion | bar: p2 w12
9 | Conclusion
9.1 | Conclusion | bar: p2 w12